## Bug
Bug/Task No | Detail | Issue Type | Status
1 | Next Button not working on Profile option | Design | In-Progress
2 | Unable to update profile | Code | Done
3 | change favicon icon | Design | Done
4 | change logo image | Design | Done
5 | Payment pop up hide when click outside | Design | Done
6 | forget password loading image | Design | Done
7 | Change in category Master. Add tax structure | Change Request | Done
8 | URL Validation. Duplicate Url saving | Code | Done
9 | Change mail setting in application | Change Request | Done
10 | Change SMS API in application | Code | In-Progress
11 | Include Term and condition page | Code | Done
12 | CP1 Data entry page with validation | Code | Done
13 | Payment functionality completion | Code | In-Progress
14 | Welcome E-mail template change | Code | Done
15 | Correction of All masters page and complete CURD operation | Code | In-Progress
16 | Changes in tax validation and implementation | Code | Done
17 | CP1 Quality development | Code | Pending
18 | CP1 Data Entry Page field changes | Change Request | Pending
19 | Dashboard development | Code | In-Progress