## Bug
Bug/Task No | Detail | Issue Type | Status
1 | Next Button not working on Profile option | Design | Pending
2 | Unable to update profile | Code | Pending
3 | change favicon icon | Design | Pending
4 | change logo image | Design | Pending
5 | Payment pop up hide when click outside | Design | Pending
6 | forget password loading image | Design | Done
7 | Change in category Master. Add tax structure | Change Request | Pending
8 | URL Validation. Duplicate Url saving | Code | Pending
9 | Change mail setting in application | Change Request | In-Progress
10 | Change SMS API in application | Code | In-Progress
11 | Include Term and condition page | Code | Pending
12 | CP1 Data entry page with validation | Code | Pending
13 | Payment functionality completion | Code | Pending
14 | Welcome E-mail template change | Code | Done
15 | Correction of All masters page and complete CURD operation | Code | In-Progress