## Bug
Bug/Task No | Detail | Issue Type | Status | owner
1 | Next Button not working on Profile option | Design | In-Progress | sunil
2 | Unable to update profile | Code | Done | sunil
3 | change favicon icon | Design | Done | saswat
4 | change logo image | Design | Done | saswat
5 | Payment pop up hide when click outside | Design | Done | saswat
6 | forget password loading image | Design | Done | saswat
7 | Change in category Master. Add tax structure | Change Request | Done | nitin
8 | URL Validation. Duplicate Url saving | Code | Done | saswat
9 | Change mail setting in application | Change Request | Done | saswat
10 | Change SMS API in application | Code | In-Progress | saswat
11 | Include Term and condition page | Code | Done | nitin
12 | CP1 Data entry page with validation | Code | Done | sunil
13 | Payment functionality completion | Code | Done | nitin
14 | Welcome E-mail template change | Code | Done | saswat
15 | Correction of All masters page and complete CURD operation | Code | In-Progress | nitin
16 | Changes in tax validation and implementation | Code | Done | nitin
17 | CP1 Quality development | Code | Pending | sunil
18 | CP1 Data Entry Page field changes | Change Request | Pending | sunil
19 | Dashboard development | Code | In-Progress | saswat
20 | Payment Email and SMS text implementation | code | Pending | Aakash | Email template and sms text is pending from SNPL end